## Slide 1: How did we get here?

## Slide 2: November 2021 email Added to Nirav’s slides – Stress/Performance test
Goal: How many patients can a site serve without significant system degradation?
1 patient = 25 orders = 4000 steps 200 patients --> 5000 orders per week --> 800,000 steps
3 shifts (over 5 days) = 24 hours * 5 = 1440 * 5 = 7200 800000 steps/7200 minutes = ~111 steps per minute.
Based on the numbers above, let’s see how we do by ramping up from 40 steps to 80 steps and then 120 steps.
Let me know your thoughts on the numbers above and also any ideas on
what recipe to use (build a new one just for this stress test or tweak an existing one?)
how will we manage manual interventions/inputs in the WF?

## Slide 3: Performance Testing Objectives
Determine if/when system issues or performance is impacted when the following activities are occurring: - All 4 activities below are concurrent, but we start small with just the 1st activity below. Agree?
Certain # of Steps/min system load (translates to # of parallel executing orders)
Generate exception detail reports
Interface activity (e.g. inventory updates from SAP)
Database backup (to generate spike in load)

## Slide 4: FYI - I am proposing that we record the following besides quantitative/objective and subjective observations by manual users who will participate as all 4 activities are running concurrently. That way we will know the threshold at which the system degrades below an acceptable limit and how we could mitigate that with additional/better hardware. Optimizing any software would be a big activity because we have many pieces and each will need to be addressed individually by checking if it adheres to best practices for application architecture, SQL optimization etc.
 | System parameters |  |  |  | 
 | Memory | CPU utilization | Hard Disk | Database | Archive/backup systems
0-15 minutes |  |  |  |  | 
15-30 minutes |  |  |  |  | 
30-45 minutes |  |  |  |  | 
45-60 minutes |  |  |  |  | 
 | Manual user observations |  |  |  | 
Quantitative |  |  |  |  | 
Subjective |  |  |  |  | 

## Slide 5: Test Setup
Set up automated performance counters to monitor infrastructure – SN – How do we do this? Log files? Any system measurement tool? Carl? Document test system’s hardware specifications. Load balanced? Hard disk, memory? How representative of production?
Generate system load automatically
Test various aspects manually
  Generate exception detail reports
  Interface activity (e.g. inventory updates from SAP)
  Database backup
  Manual workflow execution by users to observe performance – This happens in parallel to the system stress to get users’ subjective and quantitative observations.

## Slide 6: Challenges in Generating Load
In order to generate the right kind of load, we need to run a certain number of recipes in parallel to hit a target number of steps per min.
To most accurately represent the load a site will experience, we need to execute recipes that have steps in a similar arrangement to the recipes the site will be running.
In additional, manual steps will need to be executed automatically, after a random delay (tunable based on how long operators take to respond and complete a manual step).
Many manual steps require an input, that needs to be determined to ensure the recipe goes down the right branch and does not get stuck.

## Slide 7: Strategy to Generate Load
Option 1 – Site Test Environment - Reuse recipes with minor changes and existing execution data for manual inputs
Option 2 – Enterprise Environment – Build custom recipe that best represents site recipes
Automated testing service
Every # seconds, retrieve list of manual steps from list of configured workflow numbers
For each manual step, wait random delay (between # and # seconds)
Retrieve the expected input and execute step

## Slide 8: What are next steps?
Performance test coordinator (Subhash) who can:
Action | Estimated Timing
Coordinate with site and identify window of testing | Week of Jan 24th
Identify recipes for testing and reference workflows | Week of Jan 24th
Trial runs/tuning of service, total required recipe count and delays | Week of Jan 24 and Jan 31
Line up infrastructure team for performance monitoring | Week of Jan 31st
Work with infrastructure team to install custom service | Week of Jan 31st
Identify manual testers and coordinate 2-3 60 min test trials | Week of Feb 7 and Feb 14
Clean up test environment (reset equip, inventory, etc.. back to defaults) | Week of Feb 7 and Feb 14
Collect and present findings | Week of Feb 14 and Feb 21